🗺️

Herbal Remedy Advisor

Feature Roadmap

What's built, what ships with TestFlight, and what comes after

May 2026  ·  20-person Beta

This roadmap is built around one guiding principle: fewer features done exceptionally well beats more features done adequately. Every item scoped for TestFlight has been chosen because it either makes the core experience trustworthy, or because it directly serves the 20 people who will use it first. Everything else waits.

| Badge | Meaning |
| --- | --- |
| ✅ Built | Implemented and working in the current simulator build |
| 🛫 For TestFlight | Must be completed before the first TestFlight build is uploaded |
| 🔧 Polish Pass | Feature is built but needs a focused quality pass before testers see it |
| 🔮 Post-TestFlight | Deliberately deferred — not needed for a successful beta |

# 1. What's Already Built

The following features are implemented, architecturally sound, and working in the simulator. They represent the core product.

## 1.1 Core App Screens

| Screen | What It Does | Status |
| --- | --- | --- |
| Symptom Selection | 10 selectable symptom chips in a 2-column grid. Multi-select. "Find Natural Remedies" CTA. Alert if nothing is selected. | ✅ Built |
| Loading Screen | Animated spinning herb (leaf.fill SF Symbol) + "Consulting ancient herbal traditions…" pulse animation. 2-second intentional delay. | ✅ Built |
| Results Screen | Matched remedy cards with tradition-colored headers, ingredient chips, description, View Protocol + Start Journal buttons. Tradition badge row. Disclaimer footer. | ✅ Built |
| Remedy Detail Screen | Full protocol view: hero card, ingredients, about, numbered preparation steps, Day 1 wisdom quote, Begin Journal CTA, disclaimer. | ✅ Built |
| Tradition Filter Screen | Gallery of 8 traditions. Dual-mode: standalone browser (tap → detail) and filter panel (select → apply to Results). Gold ring on selected cards. Multi-select. | ✅ Built |
| Tradition Detail Screen | Full tradition view: name, region, flag image, cultural description, keyword tags. Navigated to by tapping a tradition card in the standalone Traditions tab. | ✅ Built |
| Cleanse Journal Screen | Full journal hub. All sections built (see 1.3). The most complex screen in the app. | ✅ Built |
| Day Complete Overlay | Full-screen dark overlay on mid-protocol day completion. Animated checkmark, streak pill, next-day quote preview, Continue Journey CTA. | ✅ Built |
| Protocol Complete Overlay | Full-screen congratulations on final day. Trophy badge, tradition label, stat cards, final wisdom quote, two CTAs. | ✅ Built |

## 1.2 Navigation

| Component | Detail | Status |
| --- | --- | --- |
| Root TabView | 4 tabs: Symptoms (waveform.path.ecg) / Remedies (leaf.fill) / Traditions (globe.americas.fill) / Journal (book.closed.fill). Forest green background. Active/inactive opacity. | ✅ Built |
| Auto-tab switch after analysis | RootTabView watches SymptomViewModel.isLoading. When analysis finishes, automatically switches to Remedies tab. navigateToJournalTrigger counter triggers Journal tab switch when Start is tapped. | ✅ Built |
| NavigationStack in Traditions tab | navigationDestination(for: Tradition.self) pushes TraditionDetailScreen. Back button pops cleanly. | ✅ Built |
| Tradition filter auto-clear | TraditionViewModel.clearAll() fires when a new symptom analysis starts. Stale filters never hide new results. | ✅ Built |

## 1.3 Journal Screen — Component Breakdown

| Component | Detail | Status |
| --- | --- | --- |
| Hero strip | Active protocol name, tradition label, 🔥 streak pill with contextual label (changes at 0 / 3 / 7 / 14 days). | ✅ Built |
| Summary stats bar | Days Done / Days Left / % Complete. Three cells, white card. No XP or points. | ✅ Built |
| Progress bar | Fern-to-gold gradient fill. Protocol name, percentage, Day 1 → Day N labels. Animates on appear. | ✅ Built |
| Monthly calendar | Full grid, 7 columns Su–Sa. Month navigation (‹ ›). Color-coded cells: completed (tradition fill + ✓), today (gold fill + ring), upcoming (12% tradition tint + day number), non-protocol (plain). Color legend below. | ✅ Built |
| Day Detail card | Appears inline below calendar on tap. Date, protocol day, remedy name, tradition badge, status indicator (✅/⭐/🔒/Missed). Done and today days show that day's wisdom quote. | ✅ Built |
| Today's Protocol card | Tradition-colored header, day number, checklist of up to 4 steps (tappable checkboxes). Mark Day Complete CTA. | ✅ Built |
| Daily Reminder row | Toggle switch + label "Tomorrow · 7:30 AM — Brew your tonic." UI only — no live notifications yet. | ✅ Built |
| Daily Cultural Quote card | Day N Wisdom label with tradition flag, large open-quote mark, Noto Serif italic quote, attribution (gold), context note. Rotates per day using (dayNum-1) % pool.count formula. | ✅ Built |
| Achievements row | 5 badges: First Brew (day 1), 3-Day Streak (day 3), Week One (day 7), Globe Trotter (day 14), Herb Master (1 full protocol completed). Locked = grayscale 25% opacity. | ✅ Built |
| Empty state | Journal tab shows an empty state with CTA to the Remedies tab when no protocol is active. | ✅ Built |

## 1.4 Data, Logic & Tests

| Layer | Detail | Status |
| --- | --- | --- |
| 11 remedies | 5 Ayurveda, 2 TCM, 1 Persian, 1 SE Asian Folk, 3 European. Mapped to 10 symptoms. Deduplicated on multi-symptom queries. | ✅ Built |
| 8 traditions | All with id, name, region, flag image, color, description, 4 keyword tags. One tradition (African Herbalism) added vs the original 7 in the PRD. | ✅ Built |
| 147 wisdom quotes | 21 quotes per tradition × 7 traditions. Historically sourced. Rotate deterministically by protocol day number. | ✅ Built |
| Journal persistence | 5 UserDefaults keys: remedy name, completed days, completed protocols (lifetime counter), start date, reminder toggle. Restored in JournalViewModel.init(). | ✅ Built |
| completedProtocols lifetime counter | Survives startJournal() calls. Drives Herb Master badge and the Protocol Complete overlay lifetime count. Never resets. | ✅ Built |
| 43 unit tests | JournalViewModelTests (18) — startJournal, completeDay, completion counter, computed props, persistence isolation. RemedyDatabaseTests (14) — symptom lookup, data integrity. TraditionViewModelTests (11) — toggle, clearAll, database integrity. | ✅ Built |
| Light mode lock | .preferredColorScheme(.light) on the root WindowGroup. Dark mode never renders. | ✅ Built |
| iOS 16 compatibility | All onChange(of:) calls use single-parameter form. No iOS 17+ APIs used. | ✅ Built |

🔧 Polish Pass Features that are built but need focused quality work before testers see them

# 2. Polish Pass — Built But Needs Work

These are not new features. They are areas where the foundation exists but the experience has rough edges that will be immediately noticed by people who didn't build the app. These should be addressed before the TestFlight build is archived.

| Feature | Current State | What the Polish Pass Achieves | Status |
| --- | --- | --- | --- |
| Reminder toggle — live notifications | UI is complete. Toggle switches visually. Hardcoded "7:30 AM" label. No actual notification is scheduled or cancelled. | Wire UNUserNotificationCenter behind the toggle. Request permission when first switched ON. Schedule/cancel daily notification. Show Settings deep-link if permission is denied. This makes the core retention loop real — testers will actually get the reminder. | 🔧 Wire It Up |
| Reminder time — user choice | Hardcoded to 7:30 AM everywhere. | Add a time picker (DatePicker in .graphical or .wheels style) that appears when the user taps the time. Persist hour + minute to UserDefaults. Use chosen time when scheduling the notification. | 🔧 Add Picker |
| taskChecked — persistence across kills | Task checkboxes reset to all-false if the app is killed mid-day (e.g. user checks steps 1–2, gets a call, app is killed, reopens to see unchecked steps). | Persist taskChecked to UserDefaults on every toggle. Restore in loadPersistedState(). One additional key: [userID]_journal_task_checked. | 🔧 One Key |
| start_date storage format | Stored as TimeInterval (Double). A timezone change mid-protocol shifts calendar cell alignment by a day. | Migrate to ISO 8601 date string (e.g. "2026-05-14"). Parse using Calendar.current. Run once on first launch of the updated build via a migration guard key. | 🔧 Format Fix |
| Accessibility labels | Core functionality works. Interactive elements (chips, calendar cells, achievement badges, overlay CTAs) have no accessibilityLabel or accessibilityHint. | Add descriptive labels to every tappable element. Calendar cells announce: "Day 4, Triphala cleanse, completed." Symptom chips announce: "Bloating and Gas, selected." Run Accessibility Inspector in Xcode to surface missing labels in bulk. | 🔧 Labels |
| Reduce Motion | Bounce-in and scale animations run regardless of system preference. | Read @Environment(\.accessibilityReduceMotion). When true: skip scale animations, preserve opacity fades. 3-line change per animation site. | 🔧 3 Lines |
| Font verification on device | Noto Serif and Noto Sans load correctly in Simulator because fonts exist in the dev environment. A fresh install on a physical device may fail if Info.plist registration is off. | Install on a physical iPhone that has never had the dev build. Visually confirm every screen renders the correct fonts. Check Info.plist → "Fonts provided by application" lists all .ttf files. | 🔧 Verify |

🛫 For TestFlight New features scoped for the beta — each one chosen because 20 testers need it

# 3. Features Scoped for TestFlight

These are new capabilities — not yet in the build. Each one was chosen deliberately. The test is simple: would a tester's experience be meaningfully worse without it? If yes, it's in. If no, it waits.

## 3.1 Sign in with Apple — Authentication

Full specification in 07_TestFlightAndAuth.docx, Part B. This section is the roadmap summary.

| Component | What It Does | Why It's Scoped for TestFlight |
| --- | --- | --- |
| Login screen | Full-screen forest-to-moss gradient. Leaf icon. App name + tagline. Apple sign-in button (ASAuthorizationAppleIDButton, white style). "Your data stays on your device." privacy note. | Establishes identity before the first tester session. Required groundwork for any future cloud sync. Sets a professional tone — a beta without a login screen feels unfinished. |
| Three-state machine | FIRST_TIME (no credential) → shows Login. RETURNING_AUTHENTICATED (valid credential) → skips Login, auto-enters app. RETURNING_REVOKED (credential revoked) → clears data, shows Login with expiry message. | Auto-login on every relaunch after first sign-in is the experience that feels polished. Without it, testers sign in every launch. |
| Welcome screen (first-time only) | Shown once after first sign-in. "Welcome, [First Name]." App philosophy. All 7 tradition flags in a row. "Let's Begin →" CTA. | First impression of the multicultural premise. The tradition flag row is the first time a new user understands the breadth of the app. |
| Keychain storage | Apple User ID stored in Keychain (not UserDefaults). Survives app deletion and reinstall. | UserDefaults is wiped on app deletion. A tester who deletes and reinstalls would be treated as a brand new user — losing their journal history — if the credential is in UserDefaults. |
| UserDefaults key migration | On first login: copies anonymous keys to [userID]-prefixed keys. Guards with a migration_complete flag so it runs only once. | 20 testers who used the app before login was added keep their journal progress. Without migration, their data silently disappears on first login. |

## 3.2 Launch Screen

| Component | Specification | Why It's Scoped for TestFlight |
| --- | --- | --- |
| LaunchScreen | UILaunchScreen in Info.plist. Forest green background (#1A2E1A) as a named color in Assets.xcassets. Centered leaf.fill SF Symbol in fern (#8AAB6E) at 48pt. No animation — iOS renders it statically. | TestFlight review hard-rejects builds without a launch screen. A missing launch screen also causes a visible white flash on launch, which reads as a bug to every tester. |

## 3.3 PrivacyInfo.xcprivacy

| Component | Specification | Why It's Scoped for TestFlight |
| --- | --- | --- |
| PrivacyInfo.xcprivacy | New file type added to the project target in Xcode. Declares API usage reasons: NSPrivacyAccessedAPICategoryUserDefaults (reason: CA92.1 — read/write values the app creates itself). No camera, location, contacts, or health data accessed. | Required since Spring 2024. TestFlight review rejects builds without it. This is the single highest-risk missing item in the current build. 20-minute fix. |

## 3.4 Empty States

| Screen | Empty State Trigger | Design | Status |
| --- | --- | --- | --- |
| Results Screen | User opens Remedies tab before running any symptom analysis. matchedRemedies is empty. | Centered illustration (wand.and.stars SF Symbol, 48pt, mist color). "Select your symptoms first." in Noto Serif 18pt subtext. "← Go to Symptoms" link text in sage. | 🛫 For TestFlight |

Journal empty state is already built per the Architecture Map. Results empty state is the only one missing.

## 3.5 Replace Protocol Confirmation

| Component | Behaviour | Why Scoped for TestFlight |
| --- | --- | --- |
| Replace protocol alert | When a user taps "Start Journal" on a new remedy while a protocol is already active: show a SwiftUI Alert — "Replace your current cleanse? Your progress on [Name] (Day N of M) will be lost." Two buttons: Cancel (dismisses, no change) and Replace (calls startJournal(), discarding current state). | Without this, tapping Start on a different remedy silently destroys active journal progress. A tester who accidentally taps the wrong remedy card loses days of work with no warning. This is a trust-breaking bug in a retention-focused app. |

## 3.6 Required Info.plist Keys

| Key | Value | Why Required |
| --- | --- | --- |
| NSUserNotificationUsageDescription | "Herbal Remedy Advisor sends a daily reminder to complete your cleanse protocol." | TestFlight rejects builds that call UNUserNotificationCenter without this key, even if the notification feature is never triggered during review. |
| ITSAppUsesNonExemptEncryption | NO (Boolean) | Skips the export compliance questionnaire on every upload. Without it, every archive upload shows an "Export Compliance" screen that must be answered manually. One key eliminates this permanently. |

# 4. What a Tester Will Experience, End to End

This is the intended full user journey for every one of the 20 beta testers. If every step below works correctly, the TestFlight build is a success.

| Step | Experience | Feature Behind It |
| --- | --- | --- |
| 1 | Receives TestFlight email invite. Installs the app. | Distribution setup in App Store Connect |
| 2 | Opens app. Sees a forest-green launch screen for a moment. | LaunchScreen (§3.2) |
| 3 | Login screen appears. Taps "Sign in with Apple." Face ID. Done. | Authentication (§3.1) |
| 4 | Welcome screen: "Welcome, [Name]." Sees all 7 tradition flags. Taps "Let's Begin →". | Authentication — Welcome screen (§3.1) |
| 5 | Symptom screen. Selects 2–3 things they actually feel. Taps "Find Natural Remedies." | Symptom Selection (§1.1) |
| 6 | Loading animation. Feels like it's doing something. | Loading Screen (§1.1) |
| 7 | Results appear. Sees 2–3 remedy cards with rich tradition-colored headers. | Results Screen (§1.1) |
| 8 | Taps one card to read the detail. Sees the cultural origin, steps, Day 1 quote. | Remedy Detail (§1.1) |
| 9 | Taps "Traditions" tab. Browses all 8 healing cultures. Taps one for full detail. | Tradition Filter + Detail (§1.1) |
| 10 | Returns to a remedy, taps "📓 Start." Switches to Journal tab automatically. | Auto-tab switch (§1.2) |
| 11 | Sees their journal: streak (0), calendar, today's task checklist, daily quote. | Journal Screen (§1.3) |
| 12 | Checks off the preparation steps. Taps "Mark Day Complete." | Today's Protocol card (§1.3) |
| 13 | Day Complete overlay appears. Sees ✅, streak pill (1 day), tomorrow's quote preview. | Day Complete Overlay (§1.1) |
| 14 | Tomorrow: receives a notification at their chosen time. | Live notifications (§2 Polish) |
| 15 | Opens app on Day 2. Auto-logged in. Journal shows Day 1 as ✅ in the calendar. | Auto-login + calendar persistence (§3.1, §1.3) |
| 16 | Day 2 checklist is fresh. Marks complete. Streak now 2. | Journal + persistence (§1.3, §1.4) |
| 17 | Kills app, reopens. Everything is exactly where they left it. | Persistence (§1.4) |
| 18 | Eventually completes the full protocol. Trophy overlay. Herb Master badge unlocks. | Protocol Complete Overlay (§1.1), Achievements (§1.3) |

🔮 Post-TestFlight Deliberate deferrals — these wait until beta feedback validates the direction

# 5. Deliberately Deferred

These are features that have been discussed or that a reasonable person would expect in this kind of app. They are not in scope for TestFlight. Each one has a reason.

| Feature | Why It Waits |
| --- | --- |
| Cloud sync / iCloud backup | Requires auth first (done in §3.1) but the sync itself needs server or CloudKit design. 20 testers on the same device don't need it. Validate retention first, then build sync. |
| Remedy search & browse | The 11-remedy catalog is small enough that the symptom-matching flow surfaces everything relevant. A search bar adds complexity without value until the catalog grows. |
| Additional remedies (beyond 11) | The 11 remedies are high-quality, culturally sourced, and well-tested. Adding more before beta dilutes the quality bar. Expand based on what testers ask for. |
| AI-powered remedy generation | Claude API integration was scoped for v2 in the original PRD. The static database is the right starting point — it is auditable, reliable, and not dependent on network. |
| Social sharing ("I completed Day 7") | Nice to have. Not the core value. Adds privacy surface area. Revisit after beta. |
| Apple HealthKit integration | Adds complexity and a permission request that will confuse beta testers. Revisit once the core loop is validated. |
| Ingredient sourcing / shopping links | Useful, but adds a commercial layer that isn't the point of this version. Out of scope. |
| User-submitted remedies or ratings | Requires moderation, community design, and trust infrastructure. Far out of scope. |
| iPad / landscape support | The layout was designed portrait-first. Landscape would require full re-layout of the calendar and journal. Out of scope until core is solid. |
| Dark mode | The earthy cream palette was designed for light mode. Dark mode requires a complete second palette design. Out of scope. |
| In-app purchases | No monetization in v1.0 or beta. Not a consideration until the product proves retention. |
| Practitioner connect / telemedicine | Requires third-party partnership or directory. Far future. |
| Android | iOS-first is the right strategy. Validate on one platform before expanding. |
| Onboarding tutorial screens | The Welcome screen (§3.1) plus the app's own clarity is sufficient for 20 people who know you. A full tutorial adds 2+ weeks of design and build for marginal gain. |

# 6. Recommended Build Order

Based on what is built and what needs to happen, this is the suggested sequence to reach a TestFlight-ready archive. Each phase ends with a specific exit criterion.

| Phase | Work | Exit Criterion |
| --- | --- | --- |
| Phase 1 1–2 days | Infrastructure — PrivacyInfo.xcprivacy + Launch Screen + Info.plist keys (ITSAppUsesNonExemptEncryption, NSUserNotificationUsageDescription) | App archives without warnings. Launch screen renders. PrivacyInfo.xcprivacy validates in Xcode. |
| Phase 2 3–4 days | Authentication — KeychainHelper, LoginViewModel, LoginScreen, WelcomeScreen, App entry point update, UserDefaults key migration (including start_date ISO 8601 fix and taskChecked persistence) | Fresh install: Login → Welcome → Symptom tab. Second launch: auto-login directly to app with journal restored. Sign-out via Settings.bundle works. |
| Phase 3 2–3 days | Live notifications — Wire UNUserNotificationCenter behind the reminder toggle. Time picker. Deep-link tap-to-open. Cancel on protocol complete. | Notification fires at chosen time on a physical device. Tapping it opens Journal tab. Permission-denied state shows Settings link. |
| Phase 4 1–2 days | Polish pass — Accessibility labels, Reduce Motion, taskChecked persistence (if not done in Phase 2), Results empty state, Replace Protocol alert, font verification on device. | Accessibility Inspector shows no missing labels. Notification and kill-relaunch flows verified on physical iPhone. Replace alert tested. |
| Phase 5 1 day | App Store Connect setup — App record, Beta App Description, "What to Test" notes, 20 tester emails added. | Build uploaded to App Store Connect, processed (15–30 min), and visible in TestFlight tab. Tester invites sent. |

Total estimated elapsed time from today to first TestFlight build: 8–12 days at a comfortable pace, assuming the core app is in the state described in Section 1. Phases 1 and 3 are the shortest. Phase 2 is the meatiest.

# 7. What Makes This Beta a Success

Before you send invites, decide what success looks like. This makes feedback collection purposeful and the iteration after the beta actionable.

## The Single Most Important Signal

Do testers open the app on Day 2 without a notification prompting them?

If yes, the core loop is working. The streak, the calendar filling up with their tradition's color, the quote rotating — something is pulling them back. That is the behavior that a future successful app is built on.

If no, the retention mechanism needs work regardless of how polished everything else is.

## Questions to Ask Your 20 Testers

| Question | What It Tells You |
| --- | --- |
| Which symptom did you select first, and did the matched remedy feel relevant? | Whether the symptom-to-remedy mapping resonates with real people's self-perception. |
| Did you feel like the cultural framing was respectful, or did anything feel off? | The most important qualitative signal. The app lives or dies on cultural authenticity. |
| Which daily quote stayed with you? Did any feel out of place? | Content quality signal for the 147-quote pool. |
| Did you open the app the next day without a notification? | Intrinsic retention — the most important behavioral signal in the beta. |
| Was anything confusing on first open? | UX clarity signal, especially around the Traditions tab dual-mode behavior. |
| After completing your first Day 1 — did you want to do Day 2? | Protocol commitment signal. If the answer is no, the Day Complete overlay or the streak mechanic may need rethinking. |

## Definition of a Successful Beta

- At least 10 of 20 testers complete 3 or more consecutive days on a protocol

- No tester reports feeling that a tradition was misrepresented or treated disrespectfully

- No crash bugs reported that affect core flows (symptom → results → journal)

- At least 5 testers provide written feedback beyond "looks good"

- You have a clear, prioritized list of what to fix before expanding the beta

A beta with 20 friends and family is not a product-market fit test. It is a quality and stability test. The goal is to find the things that only real users on real devices in real life will catch — not to validate the business model.

Herbal Remedy Advisor  ·  Feature Roadmap  ·  May 2026